## Slide 1: Weekly Status Report CW26
June 26th, 2026

## Slide 2: Content
Weekly Highlights / Lowlights 本周亮点 / 风险及问题
Status SN1002 / SN1003 / SN1004 SN1002 / SN1003 / SN1004 状态
Flight test program progress 飞行测试项目进展
Short term flight test plan 短期飞行测试计划

## Slide 3: Weekly Highlights / Lowlights
Highlights亮点
Considerable effort and progress has been made on ‚content freeze‘ flights to recover lost week
为了追回耽误的一周时间，在“内容冻结”飞行上做出了相当大的努力，并取得了进展
First round of budget planning has been completed
首轮预算计划已经完成
Wording of DAU SOW has been finalized with IS&S
DAU工作说明书（SOW）的文稿已与IS&S最终确认
Lowlights不足
Hydraulic Filter Package: The filter blockage / bypass indicator components do not function properly under hot weather conditions
 Parts are already changed and flight test is continouing
液压过滤组件：滤芯堵塞/旁通指示部件在高温天气条件下无法正常工作相关零件已更换，飞行测试仍在进行中
Engineers for FCS are not fully engaged in develop FECU & PTECU since export control issue is still blocked
由于出口管制问题尚未解决，飞控系统工程师未能完全投入到FECU和PTECU的开发工作中
Supplier SSP is not willing to do bug fixing on the Nose Wheel Steering Control Unit SW for free
供应商SPP不愿免费修复前轮转弯控制单元的软件漏洞
CW (Curtiss Wright) is still working on an answer when we can get the repaired DAU back
关于修复后的DAU何时能够返还一事，CW (Curtiss Wright)仍在研究中
Program risks are outlined in program risk file

## Slide 4: Status SN1002/ SN1003/ SN1004
SN1002:
      Contract for ‘trust company’ available  no management decision available  will be reported in shareholder meeting
      与飞机代持的可信公司的合同已就绪已准备就绪 → 仍待管理层决策→ 将在股东会议中汇报
      As long as this issue is not solved, SN1002 is grounded, following risks:
      若此问题不解决，SN1002只能停飞，存在如下风险
      Since we do not have a valid(!) owner, the Aircraft registration is on very high risk
      由于目前没有有效的（！）所有人，飞机注册面临极高风险
      Once the registration is lost, it would be a very high effort and very high costs to get it back into operation
      一旦注册被取消，重新恢复运行将需要极大的工作量和极高的成本
SN1003:
    Status:
      Annual inspection ongoing since aircraft is grounded due to ADAU repair (low priority)
      由于ADAU维修导致飞机停飞，年检工作正在进行中（优先级低）
      Follow-up on repair status from Procurement
      采购部关于维修状态的后续跟进
      ADAU still not repaired
      ADAU仍然没有修好
  SN1004:
    Status:
    Content freeze test flight started with one week of delay  recovery is underway
    内容冻结试飞工作已启动，较原计划延迟一周，目前正在追赶进度
No change
Needs to be solved before ferry flight
Topic for upcoming Board Meeting
无变化
需在转场飞行前解决
即将召开的董事会议题
No change since
ADAU is in repair
无变化，因为ADAU正在维修

## Slide 5: Flight Test Program Progress
Flight Test Status
Overview 26/06/26 |  | 
WEEKLY 周度 | SN1003 | SN1004
Monday 周一 | 200FH&Year Maintenance 200小时及年检维护 | 1*Flight Test Shakedown & Software Check ​1*飞行测试：系统调试与软件检查
Tuesday 周二 | 200FH&Year Maintenance 200小时及年检维护 | 2*Flight Tests SW Content Freeze 2*飞行测试：软件内容冻结
Wednesday 周三 | 200FH&Year Maintenance 200小时及年检维护 | 2*Flight Test ICS Certification+SW Content Freeze 2*飞行测试：ICS认证+软件内容冻结
Thursday 周四 | 200FH&Year Maintenance 200小时及年检维护 | 1*Flight Test VHF Certification+SW Content Freeze ​1*飞行测试：VHF认证+软件内容冻结
Friday 周五 | 200FH&Year Maintenance 200小时及年检维护 | 1*Flight Test Dual FMS for SW Content Freeze 1*飞行测试：双FMS软件内容冻结
Flight hours 飞行小时 |  |  |  |  | Flights 次数 |  |  | 
SN | 2024 | 2025 | 2026 | Total 累计 | 2024 | 2025 | 2026 | Total 累计
1002 | 49:32 | 0:00 | 0 | 1237:09 | 48 | 0 | 0 | -
1003 | 16:31 | 64:32 | 0 | 198:27 | 16 | 55 | 0 | 184
1004 | 27:52 | 80:52 | 7:28 | 116:12 | 32 | 89 | 8 | 129
Total scheduled flight hours 计划飞行总小时数 |  |  | Hours flown so far 已完成飞行小时数 |  |  |  | Percentage completed 完成百分比 |  |  |  | Hours to go (some need to be repeated) 剩余小时数 (部分需要重复进行) |  |  | 
500:00 |  |  | 314:39 |  |  |  | 63% |  |  |  | 185:21 |  |  | 
Total task items (FRQ's) scheduled 计划任务项（FRQ)总数 |  |  | FRQ's so far completed 目前已完成 |  |  |  | Percentage FRQ's completed 完成百分比 |  |  |  | FRQ's started 已开始 |  |  | 
202 |  |  | 100 |  |  |  | 50% |  |  |  | 120 |  |  | 
WEEKLY 周度 | SN1003 | SN1004
BLOCK TIME Block时间（滑出->滑入） | 00:00 | 00:45
FLIGHT TIME 飞行时间（起飞->着陆） | 00:00 | 00:00

## Slide 6: Short Term Flight Test Plan SN1003
CW 26 | Mon - 22/Jun/2026 | Tue - 23/Jun/2026 | Wed - 24/Jun/2026 | Thu - 25/Jun/2026 | Fri - 26/Jun/2026
AM | Maintenance 维护 | Maintenance 维护 | Maintenance 维护 | Maintenance 维护 | Maintenance 维护
 | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%)
PM | WOT Implementation | WOT Implementation | WOT Implementation | WOT Implementation | WOT Implementation
 | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成）
RMK |  |  |  |  | 
Annual inspection activities have low prioritiesis due to enforeced downtime caused by ADAU repair and decision not to fly
由于ADAU维修导致的强制停飞以及不飞行的决定，年检各项活动的优先级较低

## Slide 7: Short Term Flight Test Plan SN1003
CW 27 | 周一 - 29/6月/2026 | 周二 - 30/6月/2026 | 周三 - 01/7月/2026 | 周四 - 02/7月/2026 | 周五 - 03/7月/2026
AM | Maintenance 维护 | Maintenance 维护 | Maintenance 维护 | Maintenance 维护 | Maintenance 维护
 | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%) | 25FH Inspection (75%) 50FH Inspection (75%) 100FH Inspection (75%) 200FH Inspection (75%) 25/50/100/200小时定检（75%） Main and Emergency Battery Maint (95%) (will be finished before flight) 主电池及应急电池维护（95%）(飞行前完成) Scheduled Maintenance 1 Year Interval (35%) 年度计划维护(35%)
PM | WOT Implementation | WOT Implementation | WOT Implementation | WOT Implementation | WOT Implementation
 | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成） | FDR Accel Parameter - WOT 532 (0% - missing ADAU) FDR 加速度参数- WOT 532（0%，缺少ADAU) TCAS Wiring Update - WOT 536 (0%- missing ADAU) TCAS 接线更新 - WOT 536（0%，缺少ADAU) Air/water tightness - WOT 524 (0%) 气密/水密性检查 – WOT 524 (0%） EEM and MHAM Replacement - WOT 551 (waiting for material) EMM和MHAM替换 - WOT 551（等待物料） FTE Seat Re-installation (0%, will be finished after inspection) FTE 座椅重新安装(0%，将在检查后完成）
RMK |  |  |  |  | 
Annual inspection activities have low prioritiesis due to enforeced downtime caused by ADAU repair and decision not to fly
由于ADAU维修导致的强制停飞以及不飞行的决定，年检各项活动的优先级较低

## Slide 8: Short Term Flight Test Plan SN1004
CW 26 | 周一 - 22/6月/2026 | 周二 - 23/6月/2026 | 周三 - 24/6月/2026 | 周四 - 25/6月/2026 | 周五 - 26/6月/2026
AM | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试
 | Maintenance Check Flight with Emergency LDG Extension 维修检查试飞（含起落架应急放） [MAS/KON] LFTE:CCK | SW Content Freeze 软件内容冻结 [MAS/KAI] LFTE:HEN | SW Content Freeze 软件内容冻结 [MAS/KAI] LFTE:MCS | Avionics Certification for SW Content Freeze 为支持软件内容冻结而进行的航电系统认证 [MAS/KON] LFTE:STP | Dual FMS SW Content Freeze 双飞行管理系统软件内容冻结 [KAI/KON] LFTE: MCS
 | Flight Test Executed飞行测试已执行 | Flight Test Executed飞行测试已执行 | Flight Test Executed飞行测试已执行 | Flight Test Executed飞行测试已执行 | Flight Test Executed飞行测试已执行
PM | Maintenance维护 | Flight Test飞行测试 | Flight Test飞行测试 | Maintenance维护 | Maintenance维护
 | Emergency Reset WOT-200-400.130 FTE Seat Installation 应急重置 WOT-200-400.130 FTE座椅安装 | SW Content Freeze 软件内容冻结 [MAS/KAI] LFTE:STP | SW Content Freeze 软件内容冻结 [MAS/KAI] LFTE:HTR | WOT-200-400.139 Dual FMS Hyd DPI change WOT-200-400.139 双飞行管理系统 液压压差指示器更换 | HYD Filter Change 液压过滤器更换
 | Ground Test Executed地面测试已执行 | Flight Test Executed飞行测试已执行 | Flight Test Executed飞行测试已执行 |  | 
RMK | (No FTE on board during flight) Chase [TRK/HEN] （试飞期间机上无试飞工程师） 伴飞飞机[TRK/HEN] |  | ICS Certification tests are completed ICS认证测试已完成 | VHF Com short range tests are partially completed VHF通信短距测试已部分完成 | Data Evaluation for checking if additional TPs are required for Content Freeze 进行数据评估，以确定内容冻结是否需要增加额外的测试点
Annual inspection activities have low prioritiesis due to enforeced downtime caused by ADAU repair and decision not to fly
由于ADAU维修导致的强制停飞以及不飞行的决定，年检各项活动的优先级较低

## Slide 9: Short Term Flight Test Plan SN1004
CW 27 | 周一 - 29/6月/2026 | 周二 - 30/6月/2026 | 周三 - 01/7月/2026 | 周四 - 02/7月/2026 | 周五 - 03/7月/2026
AM | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试 | Flight Test飞行测试
 | SW Content Freeze Repetition Items 软件内容冻结重复项 [KAI/KON] LFTE: HTR | Avionics Certification for SW Content Freeze 为支持软件内容冻结而进行的航电系统认证 [KAI/KON] LFTE: STP | Avionics Certification for SW Content Freeze 为支持软件内容冻结而进行的航电系统认证 [KAI/KON] LFTE: STP | Stall Spot Check Items (AFT CG) 失速特性抽查测试项（后重心构型） [KAI/KON] LFTE: TRK | BACK UP Flight Test Slot for Stall 失速测试备用试飞时段
PM | Maintenance维护 | Flight Test飞行测试 | WOT Implementation WOT执行 | Flight Test飞行测试 | Paperwork文件材料
 | 10FH Inspection FTE Seat Removal 10飞行小时检查 FTE座椅移除 | Avionics Certification for SW Content Freeze 为支持软件内容冻结而进行的航电系统认证 [KAI/KON] LFTE: STP | FTE Seat Installation Ballast Installation FTE座椅安装 配重安装 | Stall Spot Check Items (AFT CG) 失速特性抽查测试项（后重心构型） [KAI/KON] LFTE: CCK | Data Evaluation 数据评估
RMK |  | XPDR&VOR Flights (No FTE on board) 应答机(XPDR)及甚高频全向信标(VOR)飞行 （机上无试飞工程师） | XPDR Flight (No FTE on board) 应答机飞行 （机上无试飞工程师） | Chase [CCK/MCS] Chase [TRK/HTR] 伴飞飞机[CCK/MCS] 伴飞飞机[TRK/HTR] | 
 |  | Overnight stay may be required at the airport 可能需要在机场过夜 |  |  | 
Annual inspection activities have low prioritiesis due to enforeced downtime caused by ADAU repair and decision not to fly
由于ADAU维修导致的强制停飞以及不飞行的决定，年检各项活动的优先级较低